## Agile User Story
PRODUCT BACKLOG/USER STORY TEMPLATE
EPIC ID | EPIC NAME OR TITLE | FEATURE ID | FEATURE | USER STORY ID | USER STORY priority either using MOSCOW or RANKING (high, medium, low) | AS A <type of user> I WANT TO <perform some task> SO THAT I CAN <achieve some goal> | ACCEPTANCE CRITERIA <GERKIN SYNTAX> | FINAL STORY ? (MEETING THE DEFINITION OF REDAY?) | SPRINT ?
EP-001 | Homepage | FR-001 | Homepage | US-001 | Must Have | AS A website visitor I WANT TO be able to type in the company's URL address into the address bar SO THAT I CAN be directed to the homepage | GIVEN that the company has a valid URL WHEN I type in the company's URL address THEN I must be directed to the homepage |  | SPRINT
|  |  |  | US-002 | Must Have | AS A website visitor I WANT TO be able to view the search bar at the top of every page the website SO THAT I CAN type information into it to search for a product or page | GIVEN that I am on the website WHEN I navigate around the website THEN the search bar must be visible on all pages |  | SPRINT
|  |  |  | US-003 | Must Have | AS AN Admin I WANT the system to display list of all countries on the website SO THAT I CAN know the country the website visitor is shopping from | GIVEN that the website visitor is on the homepage WHEN the system display the list of countries THEN the website must be able to select the country of location. |  | SPRINT
|  |  |  | US-004 | Must Have | AS A Website visitor I WANT TO be able to see the country options SO THAT I CAN select my country of location | GIVEN that I am on the website WHEN the system displays the list of countries THEN I must be able to select my country of location |  | SPRINT
|  |  |  | US-005 | Must Have | AS AN Admin I WANT the system to be able to update the website with current offers SO THAT I CAN have the current offers on the website | GIVEN that I on the backend WHEN there are current offers THEN the system must be able to update them on the website |  | SPRINT
|  |  |  | US-006 | Must Have | AS AN Admin I WANT the system to display the current offers on the homepage as a pop up SO THAT the website visitor can click on the current offer. | GIVEN that there are current offers WHEN the current offers pop up on the homepage THEN the website visitor can be able to click on those offers |  | SPRINT
|  |  |  | US-007 | Must Have | AS A website visitor I WANT TO be able to see the curernt offers pop up on the homepage SO THAT I CAN click on the current offer | GIVEN that there are current offers WHEN the offers pop up on the homepage THEN I must be able to click on the offers |  | SPRINT
|  |  |  | US-008 | Must Have | AS A Website visitor I WANT TO be able to click on the current offer pop up SO THAT I CAN be directed to the page with the discounted items | GIVEN that there is a current offer WHEN I click on the pop up THEN I must be directed to the page with the discounted items |  | SPRINT
|  | FR-002 | About us | US-009 | Must Have | AS AN Admin I WANT TO be able to edit information on the 'About Us' page SO THAT I CAN can have up to date information on the website | GIVEN that I on the backend WHEN I on the 'About Us' page THEN I must be able to edit the information on the page |  | SPRINT
|  |  |  | US-010 | Must Have | AS AN Admin I WANT TO be able to click on the 'Confirm' botton after I have made changes on the 'About Us' page SO THAT the system can update those changes | GIVEN that I have made the change on the 'About Us' page WHEN I click on the 'Confirm' botton THEN the system must update those changes |  | SPRINT
|  |  |  | US-011 | Must Have | AS A website visitor I WANT TO be able to click on the 'About Us' link SO THAT I CAN be directed to the 'About Us' page | GIVEN that I am on the website WHEN I click on the 'About Us' link THEN I must be directed to the 'About Us' page. |  | SPRINT
|  | FR-003 | Menu | US-012 | Must Have | AS AN admin I WANT the system to display the 'Menu' bar at the top of every page on the website SO THAT I CAN view the menu from any page on the website | GIVEN that I am an admin WHEN I am on any page of the website THEN I must be able to see the "Menu bar at the top of that page |  | SPRINT
|  |  |  | US-013 | Must Have | AS A website visitor I WANT TO be able to view the 'Menu' bar at the top of all pages on the website SO THAT I CAN see the menu bar from any page on the website | GIVEN that I am a website visitor WHEN I am on any page on the website THEN I must be able to view the 'Menu' bar at the top of that page |  | SPRINT
|  |  |  | US-014 | Must Have | AS AN Admin I WANT the system to be able to redirect me to the product sub categories when I click on any product category in the menu SO THAT the sub category can be visible on the website | GIVEN that I am on the backend WHEN I select a product category THEN the system must display the product sub categories on the website |  | SPRINT
|  |  |  | US-015 | Must Have | AS A website visitor I WANT the system to be able redirect to the product sub categories when I click on any product category in the menu SO THAT the sub category can be visible on the website | GIVEN that the products categories appear on the menu WHEN I select a product category THEN the system must display the product sub categories on the website |  | SPRINT
|  | FR-004 | Search | US-016 | Must Have | AS AN admin I WANT the system to respond to keyword searches SO THAT IT CAN display list of products linked to the keyword | GIVEN that the keywords has been typed in the search bar WHEN the system recognises a product that matches these words THEN the system must display list of products linked to that keyword |  | SPRINT
|  |  |  | US-017 | Must Have | AS A website visitor I WANT TO be able to type in a keyword into the search bar SO THAT I CAN be redirected to the list of products linked to that keyword | GIVEN that I have typed in a keyword in the search bar WHEN I press enter THEN I must be able to view products related to the keyword |  | SPRINT
|  |  |  | US-018 | Must Have | AS A website visitor I WANT TO be able to type in the name of a product into the search bar SO THAT I CAN be redirected to a list of product that matches my search | GIVEN that I have typed in the name of the product in the search bar WHEN I press enter THEN I must be directed to a list of product that matches my search |  | SPRINT
|  |  |  | US-019 | Must Have | AS A website visitor I WANT TO to see a display message when there are no products matching my search SO THAT I CAN type in a different product | GIVEN that I am a website visitor WHEN I search for a product AND there are no products matching my search THEN the system must display a message that "No Products Match My Search" |  | SPRINT
|  | FR-005 | Product List | US-020 | Must Have | AS AN Admin I WANT the system to be able to redirect me to the relevant products when I click on any product sub category SO THAT the relevant product list can be visible on the website | GIVEN THAT I am on the backend WHEN I select a product sub category on the sub category page THEN the system must display the relevant products on the website |  | SPRINT
|  |  |  | US-021 | Must Have | AS A website visitor I WANT the system to be able to redirect to the relevant products when I click on any product sub category on a subcategory page SO THAT the relevant products can be visible on the website | GIVEN that the products sub categories appear on the sub category page WHEN I select one of the product sub category THEN the system must display relevant products for that sub category |  | SPRINT
|  |  |  | US-022 | Must Have | AS A Website visitor I WANT to be able to click on the product sub category SO THAT I CAN view all relevant products | GIVEN that I have selected a product category WHEN I click on a product sub category THEN I must be able to view all relevant products |  | SPRINT
|  |  |  | US-023 | Must Have | AS AN Admin I WANT to be able to upload pictures of products on the website SO THAT I CAN have updated pictures of the products on the website | GIVEN that I have access to the backend WHEN I upload the picture of a product THEN the system must update the picture of the product on the website |  | SPRINT
|  |  |  | US-024 | Must Have | AS A Website visitor I WANT to be able to view the image of each product SO THAT I CAN see what the product looks like | GIVEN that I have selected a product category WHEN I click on a product sub category THEN I must be able to see the images of all relevant products |  | SPRINT
|  |  |  | US-025 | Must Have | AS A Website visitor I WANT to be able to view the name of each product under a product category SO THAT I am aware of the name of the product | GIVEN that I have selected a product category WHEN all relevant products are displayed THEN I must be able to view the names of all relavant products |  | SPRINT
|  |  |  | US-026 | Must Have | AS AN Admin I WANT to be able to update the price of a product on the website SO THAT the website can have up to date prices of all the products | GIVEN that I have access to the backend WHEN I type in a product price THEN it must be updated on the website |  | SPRINT
|  |  |  | US-027 | Must Have | AS AN Admin I WANT to be able to edit the price of a product on the website SO THAT the website can have up to date prices of all the products | GIVEN that I have access to the backend WHEN I edit the of a product THEN it must be updated on the website
|  |  |  | US-028 | Must Have | AS A Website visitor I WANT to be able to view the price of each product SO THAT I CAN know how much it cost | GIVEN that I have selected a product category WHEN I click on a product under that category THEN I must be able to view the price of the product |  | SPRINT
|  |  |  | US-029 | Must Have | AS AN Admin I WANT the system to display the full detail of a product on the website SO THAT I CAN view everything about the product | GIVEN THAT I have selected the image of the product WHEN I click on the image THEN I must be redirected to view everything about the product |  | SPRINT
|  |  |  | US-030 | Must Have | AS A website visitor I WANT TO be able to click on the image of each product SO THAT I CAN be redirected to the 'product preview' page | GIVEN that I have selected a product sub category WHEN I click on the product image THEN I must be redirected to the 'product preview' page
|  |  |  | US-031 | Should Have | AS AN admin I WANT the system to be able to delete product information on the website SO THAT I CAN remove the product from the product catalog on the website | GIVEN that I can access the backend WHEN I delete the product information THEN the deleed product should be removed from the product catalog on the website |  | SPRINT
|  | FR-006 | Product Filter | US-032 | Must Have | AS AN Admin I WANT the system to display filter options on the left hand side of the product page SO THAT I CAN filter my search from the product page | GIVEN that I am on the product page WHEN I see the filter fucntion on the left hand side of the product page THEN I must be able to filter my search from the page |  | SPRINT
|  |  |  | US-033 | Must Have | AS A website visitor I WANT TO be able to see the filter options on the left hand side of the products page SO THAT I CAN filter my search from the product page | GIVEN that I am on the product page WHEN I see the filter fucntion on the left hand side of the product page THEN I must be able to filter my search from the page |  | SPRINT
|  |  |  | US-034 | Must Have | AS AN Admin I WANT the system to display only the products relating to the filter selected SO THAT the products can be viewed on the website | GIVEN that I have access to the backend WHEN I select the products relating to the filter selected THEN the products relating to the filter selected must be displayed on the website |  | SPRINT
|  |  |  | US-035 | Must Have | AS A website visitor I WANT TO be able to filter the product list by price, product type, ratings SO THAT I CAN narrow down my search | GIVEN that I have selected a filter option WHEN I click on apply filter THEN I must be able to view only the related products |  | SPRINT
|  |  |  | US-036 | Must Have | AS AN Admin I WANT the system to enable the 'Clear filter' option SO THAT all available products can be displayed on the website | GIVEN that I have selected 'Clear filter' option WHEN I click on it THEN the system must display all available products on the website |  | SPRINT
|  |  |  | US-037 | Must Have | AS A website visitor I WANT the system to enable the 'Clear filter' option SO THAT all available products can be displayed on the website | GIVEN that I have selected 'Clear filter' option WHEN I click on it THEN the system must display all available products on the website |  | SPRINT
|  | FR-008 | Shopping Cart | US-038 | Must Have | AS AN Admin I WANT the to be able to view the 'Shopping Cart' icon at the top of every page on the website SO THAT I CAN see the shopping cart icon on every page | GIVEN that I am on the website WHEN I navigate through the pages THEN I must be able top view the 'Shoping Cart' on the top of every page |  | SPRINT
|  |  |  | US-039 | Must Have | AS A website visitor I WANT TO be able to see the shopping cart icon at the top right corner of every page at all times SO THAT the cart icon can be visible at all times | GIVEN that I am on the website WHEN I navigate around the webiste THEN I shoud be able to see the shopping cart icon at the top right corner of every page |  | SPRINT
|  |  |  | US-040 | Must Have | AS AN Admin I WANT the system to display the number of items in the shopping cart SO THAT the number of items in the cart can be visible at all times | GIVEN that I there are items added to the shopping cart WHEN I click on the shopping cart THEN I must be able to see the number of items in the shopping cart at all times |  | SPRINT
|  |  |  | US-041 | Must Have | AS A website visitor I WANT the system to display the number of items in the shopping cart SO THAT the number of items in the cart can be visible at all times | GIVEN that I have added items to the shopping cart WHEN I click on the shopping cart THEN I must be able to see the number of items in the shopping cart at all times |  | SPRINT
|  |  |  | US-042 | Must Have | AS AN Admin I WANT the system to be able to add items to the shopping cart SO THAT I CAN be aware of items added to the shopping cart | GIVEN that I am an admin WHEN an item is added to the shopping cart THEN the system must authenticate it GIVEN I am an admin WHEN the 'add to cart' button is clicked THEN the item must be added to shopping cart |  | SPRINT
|  |  |  | US-043 | Must Have | AS A website visitor I WANT TO be able to add items to the shopping cart SO THAT I CAN continue to purchase the item | GIVEN thati have selected an item WHEN I add the item to the sopping cart THEN I must be able to continue to make a purchase for the item in the shopping |  | SPRINT
|  |  |  | US-044 | Must Have | AS AN Admin I WANT the system to be able to remove items from the shopping cart SO THAT I can be aware the number of items in the shopping cart | GIVEN that an item has been removed from the shopping cart WHEN the system authenticates it THEN I must be aware of number of items in the shopping cart |  | SPRINT
|  |  |  | US-045 | Must Have | AS A website visitor I WANT to be able to remove items from the shopping cart SO THAT I can continue with my purchase | GIVEN that an item is in the shopping cart WHEN I remove the item from the shopping cart THEN I must be able to continue with my purchase |  | SPRINT
|  |  |  | US-046 | Must Have | AS AN Admin I WANT to be able to view the quantity of item in the shopping cart SO THAT I CAN see the number of products in the shopping cart | GIVEN that there are items in the shopping cart WHEN I click on the 'Shopping cart' button THEN I must be able to see the number of products in the shopping cart |  | SPRINT
|  |  |  | US-047 | Must Have | AS A website visitor I WANT TO be able to be add multiple items to the shopping cart SO THAT I CAN purchase multiple items at the same time | GIVEN that I have selected some items WHEN I add these items to the shopping cart THEN I must be able to purchase multiple items at the same time |  | SPRINT
|  |  |  | US-048 | Must Have | AS AN admin I WANT to be able to view saved items in the shopping cart SO THAT I CAN be aware of items that have been saved in the shopping cart | GIVEN that there are saved items in the shopping cart WHEN I click on 'Shopping cart' THEN I must be aware of items saved in the shopping cart |  | SPRINT
|  |  |  | US-049 | Must Have | AS A registered user I WANT TO be able to save items in the shopping cart for later SO THAT I CAN conclude my shopping at a later date | GIVEN that I have added items to the shopping cart WHEN I save these items for later date THEN I must be able to conclude my shopping at a later date |  | SPRINT
|  | FR-009 | Contact Us | US-050 | Must Have | AS AN admin I WANT the system to display the "Contact Us" link at the footer of all pages on the website SO THAT I CAN see the "Contact Us" link at the bottom of every page | GIVEN that the website have a 'Contact Us' link at the footer of every page WHEN I navigate through the website THEN I must be able to see the contact us link at the footer of every page on website |  | SPRINT
|  |  |  | US-051 | Must Have | AS A website visitor I WANT to be able to see the "Contact Us" link at the footer of all pages on the website SO THAT I do not have to navigate to away from the page to contact the company | GIVEN that the 'Contact Us' link is at footer of very page WHEN I to contact the company THEN I must be able to use the 'Contact Us' link from the footer of any page on the website |  | SPRINT
|  |  |  | US-052 | Must Have | AS AN admin I WANT to be able to view a completed contact us form SO THAT I CAN respond to customers query | GIVEN that there is a completed contact us form WHEN the I clicks on the "Contact Us" link THEN I must be able to respond to customers' query |  | SPRINT
|  |  |  | US-053 | Must Have | AS A website visitor I WANT to be able to click on the 'Contact Us' link SO THAT I CAN view the company's contact information | GIVEN that I am at the footer of any page WHEN I click on the 'Contact Us' link THEN I must be redirected to a page that will show the company's contact information |  | SPRINT
|  |  |  | US-054 | Must Have | AS AN admin I WANT to be able to edit the 'Contact Us' information SO THAT I CAN update the information in the 'Contact Us' | GIVEN that I am at the backend WHEN I edit the information in the 'Contact Us' link THEN I must be able to update the information in the 'Contact Us' |  | SPRINT
|  | FR-010 | Customer Chat Support | US-055 | Should Have | AS AN Admin I WANT to be able to see the customer chat support icon on every page SO THAT I CAN respond to enquiries at all times | GIVEN that I am an Admin WHEN I see the customer chat support on every page of the website THEN I should be able to respond to enquiries at all times |  | SPRINT
|  |  |  | US-056 | Should Have | AS A Website visitor I WANT to be able to view the customer chat support icon on every page on the website SO THAT I CAN send my enquiries from any page of the website | GIVEN that I am on the website WHEN I see the customer chat support icon THEN I should be able to send my enquiries from any page of the website |  | SPRINT
|  |  |  | US-057 | Should Have | AS AN Admin I WANT to be able receive queries in real-time SO THAT I can respond to them on time | GIVEN that I a query has been sent WHEN I receive the query THEN I should be able to respond to it in real-time |  | SPRINT
|  |  |  | US-058 | Should Have | AS A Website visitor I WANT to be able to click on the customer chat support icon SO THAT I CAN send to my queries to the company | GIVEN that I am on the website WHEN I click on on the customer chat support THEN I should be able to send my queries to the company |  | SPRINT
|  |  |  | US-059 | Should Have | AS AN Admin I WANT the system to be able to manage users data SO THAT I CAN comply with GDPR laws | GIVEN that users have supplied their data on the website WHEN the system receive these data THEN the system must comply with the GDPR laws |  | SPRINT
|  | FR-011 | Social Media Intergration | US-060 | Must Have | AS AN Admin I WANT the system to display the Snapchat icon on the footer of every page SO THAT I CAN click on it and be redirected to the company's Snapchat page | GIVEN that the Snapchat icon is on the footer of every page WHEN I click on it THEN I must be redirected to the Snapchat page of the company |  | SPRINT
|  |  |  | US-061 | Must Have | AS A Website visitor I WANT to be able to view the Snapchat icon on the footer of every page SO THAT I CAN click and be redirected to the company's Snapchat page | GIVEN that I can view the Snapchat icon on the footer of every page WHEN I click on it THEN I must be redirected to the company's Snapchat page |  | SPRINT
|  |  |  | US-062 | Must Have | AS AN Admin I WANT the system to display the Instagram icon on the footer of every page SO THAT I CAN click on it and be redirected to the company's Instagram page | GIVEN that the Instagram icon is on the footer of every page WHEN I click on it THEN I must be redirected to the Instagram page of the company |  | SPRINT
|  |  |  | US-063 | Must Have | AS A Website visitor I WANT to be able to view the Instagram icon on the footer of every page SO THAT I CAN click and be redirected to the company's Instagram page | GIVEN that I can view the Instagram icon on the footer of every page WHEN I click on it THEN I must be redirected to the company's Instagram page |  | SPRINT
|  | FR-012 | Terms and Conditions | US-064 | Must Have | AS AN admin I WANT to able to view the company's Terms & Conditions on the footer of every page SO THAT I CAN be aware of the Terms & Conditions | GIVEN that I am on the website WHEN I scroll to the bottom of every page THEN I must be able to see the Terms & Conditions |  | SPRINT
|  |  |  | US-065 | Must Have | AS A website visitor I WANT to able to view the company's Terms & Conditions on the footer of every page SO THAT I CAN be aware of the Terms & Conditions | GIVEN that I am on the website WHEN I scroll to the footer of the page THEN I must be able to view the Terms & Conditions |  | SPRINT
|  |  |  | US-066 | Must Have | AS A website visitor I WANT to able to click on the Terms & Conditions SO THAT I CAN read the Terms & Conditions | GIVEN that I am on the footer of the page WHEN I click on the Terms and Conditions THEN I must be able to read the Terms & Conditions |  | SPRINT
|  |  |  | US-067 | Must Have | AS AN Admin I WANT to be able to edit the Terms & Conditions SO THAT the website can have an up to date Terms & Conditions | GIVEN that I can access the backend WHEN I edit the Terms & Condition THEN the website must be able to have an up to date Terms & Condition |  | SPRINT
|  | FR-013 | Feedback | US-068 | Must Have | AS AN admin I WANT the system to display the product rating icon on the website SO THAT the product ratings icon can be visible at all times | GIVEN that I am on the website WHEN I navigate through the pages THEN the product rating icon must be visible at all times |  | SPRINT
|  |  |  | US-069 | Must Have | AS A Registered customer I WANT to be able to rate a product after I have purchase the product SO THAT I CAN share my ratings of the product on the website | GIVEN that I am on the website WHEN I purchase a product THEN I must be able to rate the product on the website |  | SPRINT
|  |  |  | US-070 | Must Have | AS AN Admin I WANT the system to display the "Review" button on the website SO THAT it can be visible on the website | GIVEN that I am an admin WHEN the system display the "Review" button on the website THEN it must be visible at all times |  | SPRINT
|  |  |  | US-071 | Must Have | AS A Registered customer I WANT to be able to write a review about my shopping experience on the website SO THAT I CAN share my experience | GIVEN that I am a Registered customer WHEN I write my shopping review on the website THEN I must be able to share my experience |  | SPRINT
|  |  |  | US-072 | Must Have | AS AN admin I WANT the system to notify me of the latest reviews SO THAT I CAN be aware of the latest reviews | GIVEN that I can access the backend WHEN there are latest reviews THEN the system must notify me |  | SPRINT
EP-002 | Sign up/Sign in | FR-014 | Sign Up | US-073 | Must Have | AS AN Admin I WANT to be able to sign up on the website SO THAT I CAN create my own unique account | GIVEN that I an admin WHEN I am on the website THEN I must be able to create my own unique account |  | SPRINT
|  |  |  | US-074 | Must Have | AS A website visitor I WANT to be be able to sign up on the website SO THAT I CAN create a customer account | GIVEN that I am on the website WHEN I sign up THEN I must be able to create a customer account GIVEN that there is a sign up botton on the website WHEN I click on 'Sign Up' THEN I must be able to fill the sign up form to create a customer account |  | SPRINT
|  |  |  | US-075 | Must Have | AS A website visitor I WANT to be be able to submit the completed sign up form SO THAT I CAN know that my sign up is successful | GIVEN that I have filled the sign up form WHEN I submit the completed sign up form THEN my sign up must be successful |  | SPRINT
|  |  |  | US-076 | Must Have | AS AN Admin I WANT the system to display the reCAPTCHA verification SO THAT it can verify the person person signing up | GIVEN that there is a reCAPTCHA on the website WHEN a website visitor sign to become a customer THEN the reCAPTCHA must verify the person |  | SPRINT
|  |  |  | US-077 | Must Have | AS A Website visitor I WANT to see the reCAPTCHA verification displayed SO THAT I CAN complete my sign up | GIVEN than I am a website visitor WHEN I am on the sign up page THEN I must be able to see the reCAPTCHA verification GIVEN than I am on the sign up page WHEN I click the reCAPTCHA verification THEN I must be able to complete my sign up |  | SPRINT
|  |  |  | US-078 | Must Have | AS A website visitor I WANT to be able to accept the "Terms & Conditions" SO THAT I CAN proceed to sign up as a Registered customer | GIVEN that I am on the sign up page WHEN I accept the Terms & Conditions THEN I must be able to proceed to sign up as a Registered customer |  | SPRINT
|  |  |  | US-079 | Must Have | AS AN Admin I WANT to be notified when someone creates a new account on the website SO THAT I CAN be aware of the new account | GIVEN that I can access the backend WHEN someone creates a new account on the website THEN I must be notified |  | SPRINT
|  | FR-015 | Sign In | US-080 | Must Have | As A Registered customer I WANT to be able to sign in to my account SO THAT I CAN access my account | GIVEN that I have the right login credentials WHEN I sign in in to my account THEN I must be able to access my account. |  | SPRINT
|  |  |  | US-081 | Must Have | AS AN Admin I WANT the system to display an error message when someone try to login with an incorrect login credentials SO THAT I can be aware that someone tried to sign in with an incorrect login credentials | GIVEN that someone tried to sign in with an incorrect login credentials WHEN the system flags the inceorrect loging activity AND the system displays the error message THEN I must be aware that someone tried to login with an incorrect login credentials |  | SPRINT
|  |  |  | US-082 | Must Have | AS A Registered customer I WANT an error message to pop up when sign in with an incorrect login credentials SO THAT I CAN be redirected to login with the correct login credentials | GIVEN that I am a Registered Customer WHEN I login with an incorrect login credentials AND error message pops up THEN I must be redirected to login with the correct login credentials |  | SPRINT
|  |  |  | US-083 | Must Have | As A Registered customer I WANT to be able to click the 'sign out' button SO THAT I CAN sign out of my account | GIVEN that I am a Registered customer WHEN I click the 'sign out' button THEN I must be able to sign out of my account
|  | FR-016 | Password reset | US-084 | Must Have | AS AN Admin I WANT the system to send a reset password link to my email SO THAT I CAN reset my password | GIVEN that I am an admin WHEN the system send the reset password link to my email THEN I must be able to reset my password via the link |  | SPRINT
|  |  |  | US-085 | Must Have | AS A Registered customer I WANT to be able to reset my password SO THAT I CAN access my account | GIVEN that I am a Registered customer WHEN I receive the password reset link in my email THEN I must be able to reset my password GIVEN that I am a Registered customer WHEN I click the password reset link THEN I must be able to create a new password GIVEN that I am a Registered customer WHEN I enter my new password THEN the system must update my account GIVEN I have reset my password to a new password WHEN I type in my new password THEN the system must grant me access to my account |  | SPRINT
|  |  |  | US-086 | Must Have | AS AN Admin I WANT to be able to see the "Forgotten Password" tab the bottom of the sign in tab SO THAT I CAN be able to create a new password | GIVEN that I have forgotten my password WHEN I click on the "Forgotten Password" tab THEN I must be able to create a new password |  | SPRINT
|  |  |  | US-087 | Must Have | AS A Registered customer I WANT TO be able to click on the "Forgotten Password " tab SO THAT I CAN create a new password | GIVEN that I am a Registered customer WHEN I click on the "Forgotten Password" tab THEN I must receive a password reset link in my email GIVEN that I have a registered with a valid email address WHEN I receive the password reset link THEN I must be able to create a new password GIVEN that I have created a new password WHEN I type in to the system THEN I must be able to login with my new password |  | SPRINT
|  | FR-017 | Notifications | US-088 | Must Have | AS AN Admin I WANT to be notified when a website visitor sign up to become a Registered customer SO THAT I CAN be aware that someone has signed up to become a Registered Customer | GIVEN that I am an admin WHEN a website visitor sign up to become a Registered customer THEN I must be notified |  | SPRINT
|  |  |  | US-089 | Must Have | AS A Website visitor I WANT to be receive an email notification when I sign up on the website SO THAT I CAN know that my sign up was successful | GIVEN that I am a website visitor WHEN I sign up on the website THEN I must be able to receive an email notification that my sign up was successful |  | SPRINT
|  |  |  | US-090 | Must Have | AS AN Admin I WANT the system to notify me when an order is placed SO THAT I CAN know that an order has been placed | GIVEN that I am an admin WHEN an order is placed on the website THEN the system must notify me |  | SPRINT
|  |  |  | US-091 | Must Have | AS A Registered customer I WANT to be able to receive an email notification when I place an order SO THAT I CAN know that my order was successful | GIVEN that I am a Registered customer WHEN I place an order THEN I must receive an email notification that my order was successful |  | SPRINT
|  |  |  | US-092 | Must Have | AS A website visitor I WANT to be able to receive an email notification when I place an order SO THAT I CAN know that my order was successful | GIVEN that I am a website visitor WHEN I place an order THEN I must receive an email notification that my order was successful |  | SPRINT
|  |  |  | US-093 | Must Have | AS AN Admin I WANT the system to notify me when an order has been despatched SO THAT I CAN know that the order has been despatched | GIVEN that I can access backend WHEN an order has been despatched THEN the system must notify me |  | SPRINT
|  |  |  | US-094 | Must Have | AS A Registered customer I WANT the system to notify me when my order has been despatched SO THAT I CAN know that my order has been despatched | GIVEN that I have placed an order WHEN the order has been despatched THEN I must be notified that my order has been despatched |  | SPRINT
EP-003 | Online Payment | FR-018 | Online Payment | US-095 | Must Have | AS AN Admin I WANT the system to display "Continue as a guest" button SO THAT it can be visible on the check out page | GIVEN that there is a "Continue as a guest" button on the website WHEN the system displays it THEN it must be visible on the checkout page |  | SPRINT
|  |  |  | US-096 | Must Have | AS A website visitor I WANT to be able to click on the "Continue as a guest" button SO THAT I CAN make a purchase without registering to become a customer | GIVEN that I am a website visitor WHEN I click on the "Continue as a guest" button THEN I must be able to make payment without registering to become a customer |  | SPRINT
|  |  |  | US-097 | Must Have | AS AN website visitor I WANT to be able to pay for my items as a guest on the website SO THAT I CAN purchase items without registering to become a customer | GIVEN that I am a website visitor WHEN I purchase an item THEN I must be able to make payment without registering to become a customer |  | SPRINT
|  |  |  | US-098 | Must Have | AS AN Admin I WANT the system to display an error message when someone type in incorrect bank details SO THAT I CAN be aware that the bank details are incorrect | GIVEN that I can access the backend WHEN when someone type in an incorrect bank details THEN the system must display an error message |  | SPRINT
|  |  |  | US-099 | Must Have | AS A website visitor I WANT the system to notify me when I type in an incorrect bank details SO THAT I CAN be redirected to type in the correct banck details | GIVEN that I have typed in an incorrect bank details WHEN the system notifies me THEN I must be redirected to type in the correct bank details |  | SPRINT
|  |  |  | US-100 | Must Have | AS AN Admin I WANT the system to display the "Save payment details" tab SO THAT I CAN it can be visible on the website | GIVEN that I can access the backend WHEN the system display the "Save payment details" tab THEN it must be visible at all times on the website |  | SPRINT
|  |  |  | US-101 | Must Have | AS AN Registered customer I WANT to be able to save my payment details on the website SO THAT I do not have to type it in everytime I make a purchase | GIVEN that I am a Registered customer WHEN I have saved my payment details on the website THEN I do not have to type it in wheneve I want to make subsequent purchase |  | SPRINT
|  |  |  | US-102 | Must Have | AS A Registered customer I WANT to be able to login to my account at the point of checkout SO THAT I CAN pay using my saved payment details. | GIVEN that I am on the checkout page WHEN I login in to my account THEN I must be able to make payment using my saved payment details |  | SPRINT
|  |  |  | US-103 | Must Have | AS AN Admin I WANT the system to display the "Add new payment details" tab SO THAT it can be visible on the website at all times | GIVEN that I can access the backend WHEN the system display the "Add new payment details THEN it must be visible on the website at all times |  | SPRINT
|  |  |  | US-104 | Must Have | AS AN Admin I WANT to be notified when someone adds/updates new payment details on the website SO THAT I CAN be aware that new payment details have been added/updated | GIVEN that I can access the backend WHEN someone adds/updates new payment details on the website THEN I must be notified |  | SPRINT
|  |  |  | US-105 | Must Have | AS A Registered customer I WANT to be able to add new/update payment details on the website SO THAT I CAN have an up to date payment details on the website | GIVEN that I am a Registered customer WHEN I add new/update payment details on the website THEN my payment details must be up to date |  | SPRINT
|  |  |  | US-106 | Must Have | AS A Registered customer I WANT to be notified by email when I add new/update payment details on the website SO THAT I CAN be assured that the system have accepted the newly added/updated bank details | GIVEN that I am a Registered customer WHEN I add new/update payment details on the website THEN I must be notified by email |  | SPRINT
|  |  |  | US-107 | Must Have | AS AN Admin I WANT the system to display the secure payment options SO THAT it can be visible on the website at all times | GIVEN that I can access the backend WHEN the system display the secure payment options THEN it must be visible on the website at all times |  | SPRINT
|  |  |  | US-108 | Must Have | AS A Website visitor I WANT to be able to see the secure payment options icon on the website SO THAT I CAN be aware of the payment options availabe | GIVEN that I am am on the website WHEN I navigate to the checkout page THEN I must be able to see the secure payment options icon |  | SPRINT
|  |  |  | US-109 | Must Have | AS A website visitor I WANT to be able to pay for an item using one of the secure payment options SO THAT I CAN select my prefered payment option | GIVEN that there are payment options on the website WHEN I see the payment options available THEN I must be able to select my prefered payment option |  | SPRINT
|  |  |  | US-110 | Must Have | AS AN Admin I WANT the system to be able to redirect me to 3D secure payment page when I click on the 'pay' button SO THAT I CAN view the 3D secure payment page | GIVEN that I can access to the backend WHEN I click on the 'pay' button THEN I must be able to view the 3D secure payment page
|  |  |  | US-111 | Must Have | AS A Website visitor I WANT TO be redirected to the 3D secure payment page when I click on the 'pay' button SO THAT I CAN complete my payment | GIVEN that I have clicked on the 'pay' button WHEN the system redirects me to the 3D secure payment page THEN I must be able to complete my payment
|  |  |  | US-112 | Must Have | AS An Admin I WANT the system to generate receipts for every purchase on the website SO THAT I CAN be aware of the purchase | GIVEN that I can access the backend WHEN someone makes a purchase on the website THEN the system must generate receipts |  | SPRINT
|  |  |  | US-113 | Must Have | AS A Registered customer I WANT to be able to recieve a receipt for my purchase via my email SO THAT I CAN have a record of my pruchase | GIVEN that I have supplied a valid email address WHEN I make a purchase on the website THEN I must be able to receive a receipt via my email |  | SPRINT
|  |  |  | US-114 | Must Have | AS A website visitor I WANT to be able to recieve a receipt for my purchase via my email SO THAT I CAN have a record of my purchase | GIVEN that I have supplied a valid email address WHEN I make a purchase on the website THEN I must be able to receive a receipt via my email |  | SPRINT
|  |  |  | US-115 | Must Have | AS AN Admin I WANT the system to display the currency based on the country of location SO THAT purchases can be made on the website with the local currency | GIVEN that the website display list of the all the currency of the countries WHEN a country of location is selected THEN the local currency of the country must be visible on the website |  | SPRINT
|  |  |  | US-116 | Must Have | AS A Website visitor I WANT TO be able to select the currency of my country of location SO THAT I CAN purchase products in my local currency | GIVEN that the name of my country of location is on the website WHEN I select my country of location THEN I must be able to purchase products in my local currency |  | SPRINT
|  |  |  | US-117 | Must Have | AS A Registered customer I WANT TO be able to select the currency of my country of location SO THAT I CAN purchase products in my local currency | GIVEN that the name of my country of location is on the website WHEN I select my country of location THEN I must be able to purchase products in my local currency |  | SPRINT
EP-004 | Dashboard | FR-019 | Dashboard | US-118 | Must Have | AS AN Admin I WANT to be able to customise my profile on the admin dashboard SO THAT I CAN have my own unique profile on the website | GIVEN that I am on the admin dashboard WHEN I customise my profile on the website THEN I must be able to have my own unique profile |  | SPRINT
|  |  |  | US-119 | Must Have | AS A Registered customer I WANT to be able to customise my profile on the customer dashboard SO THAT I CAN I have my own unique profile on the website | GIVEN that I am on the customer WHEN I customise my profile on the website THEN I must be able to my own unique profile |  | SPRINT
|  |  |  | US-120 | Must Have | AS A Registered customer I WANT to be able to edit my profile on the website SO THAT my information on the website can be up to date | GIVEN that I am a Registered customer WHEN I edit my profile on the website THEN my information must be up to do date |  | SPRINT
|  |  |  | US-121 | Must Have | AS A Registered customer I WANT to be able to update my profile on the website SO THAT my information on the website can be up to date | GIVEN that I am a Registered customer WHEN I update my profile on the website THEN my information must be up to do date |  | SPRINT
|  |  |  | US-122 | Must Have | AS AN Admin I WANT to be able to view saved items on the website SO THAT I CAN be aware of the saved items | GIVEN that I am on the backend WHEN items are saved on the website THEN I must be able to view the saved items |  | SPRINT
|  |  |  | US-123 | Must Have | AS A Registered customer I WANT to be able to save items to my Favourites/Wishlists SO THAT I CAN continue with my order at a later date | GIVEN that I am a Registered customer WHEN I saved items to my Favourites/Wishlists THEN I must be able to continue with my order at a later date |  | SPRINT
|  |  |  | US-124 | Must Have | AS AN Admin I WANT to be able to view order history SO THAT I CAN view all previous orders | GIVEN that I can access backend WHEN I click on order history THEN I must be able to view all previous orders |  | SPRINT
|  |  |  | US-125 | Should Have | AS A Registered customer I WANT to be able to view my order history SO THAT I am aware of all my previous purchases on the website | GIVEN that I am a Registered customer WHEN I click on my order history THEN I must be able to view all my previous purchases |  | SPRINT
|  |  |  | US-126 | Should Have | AS AN Admin I WANT the system to notify me about all abandoned shopping carts on the website SO THAT I can be aware of the abandoned shopping cart | GIVEN that there is an abandoned shopping cart WHEN the system notifies me THEN I should be aware about the abandoned shopping cart |  | SPRINT
|  |  |  | US-127 | Must Have | AS AN Admin I WANT the system to notify me when I need to restock an item on the website SO THAT I CAN be aware of the items that need restocking | GIVEN that I am an Admin WHEN an item needs restocking THEN the system must notify me |  | SPRINT
|  |  |  | US-128 | Should Have | AS AN Admin I WANT to be able to view the most recent orders SO THAT I CAN be aware of these most recent orders | GIVEN that there are most recent orders WHEN I view these orders THEN I should be aware of these most recent orders |  | SPRINT
|  |  |  | US-129 | Should Have | AS AN Admin I WANT to be able to view the traffic on the website SO THAT I CAN measure the usage on the website | GIVEN that I can access the backend WHEN there is traffic on the website THEN I should be able to measure the usage |  | SPRINT

## Sheet1
AGILE USER STORY TEMPLATE
EPIC ID | EPIC NAME OR TITLE | FEATURE ID | FEATURE | USER STORY ID | USER STORY PRIORITY | AS A <type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal> | ACCEPTANCE CRITERIA <GERKIN SYNTAX>
EP-001 |  | FR-001 |  | US-001 | High |  | View a status report from each team member | Ensure the project stays on track | GIVEN WHEN THEN GIVEN WHEN THEN
EP-001 |  | FR-002 |  | US-002 | Low |  | Be reminded of upcoming deadlines | Complete my tasks on time
EP-001 |  | FR-003 |  | US-003 | Medium |  | See the big-picture view of department work | Stay in the loop
EP-002 |  | FR-004 |  | US-004 | Medium
EP-002 |  | FR-005 |  | US-005 | Medium
EP-002 |  | FR-006 |  | US-006 | Medium
EP-003 | PURCHASE | FR-007 | CHECKOUT
EP-003 | PURCHASE | FR-008 | CART
EP-003 | PURCHASE | FR-009 | PAYMENT
EP-003 | PURCHASE | FR-010 | PAYMENT GATEWAY